## Slide 1
M.Tech Program
Advanced Industry Integrated Programs
Jointly offered by University and LTIMindTree
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System
Nandana Jayan
Knowledge partner | Implementation partner

## Slide 2
Analyzes construction schedule disruptions such as activity delays and resource shortages.
Identifies affected activities and determines their impact on the overall project completion.
Generates and optimizes recovery strategies using Agentic AI and OR-Tools.
Recommends the best recovery plan and provides an understandable explanation using an LLM.
Introduction
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 3
Detect and analyze the impact of construction schedule disruptions on project activities.
Identify affected activities and dependencies to determine potential project delays.
Generate and optimize recovery strategies considering time, resources, and scheduling constraints.
Recommend the most suitable recovery plan with an explainable, evidence-based justification.
Objectives
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 4
Covers construction project schedule analysis using activities, durations, dependencies, and resource constraints.
Handles disruptions such as activity delays and resource shortages and identifies their impact on downstream activities.
Generates and evaluates alternative recovery strategies using constraint-based optimization.
Provides an explainable recovery recommendation through an Agentic AI workflow and LLM-based explanation.
Scope
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 5
Resource-Constrained Project Scheduling Problem (RCPSP) research addresses scheduling activities under precedence and limited-resource constraints.
Construction scheduling research applies resource-constrained scheduling to model complex activity dependencies and resource limitations.
Existing delay-analysis approaches study the effect of disruptions on project schedules, but dynamic schedule recovery remains challenging.
Recent AI-based approaches combine prediction, simulation, and optimization for schedule resilience and recovery, with challenges in interpretability and practical integration.
Literature Review
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 6
Existing research provides established methods for project scheduling, resource allocation, delay analysis, and schedule optimization.
Most approaches focus on optimizing a schedule or analyzing delays rather than providing an integrated recovery decision-support workflow.
There is an opportunity to combine disruption impact analysis, automated recovery-plan generation, constraint-based optimization, and explainable AI.
The proposed system follows: Disruption → Impact Analysis → Recovery Options → OR-Tools Optimization → Best Plan → LLM Explanation.
Summary of Literature
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 7
Dataset & Scenarios: Uses PSPLIB J30 scheduling data with controlled construction-style disruptions such as activity delays and resource shortages.
Impact & Recovery: Identifies affected activities and generates multiple feasible recovery strategies based on dependencies and resource constraints.
Agentic Optimization: Uses LangGraph to coordinate the workflow and OR-Tools to evaluate and optimize alternative recovery schedules.
Explainable Decision Support: Uses an LLM to explain the recommended recovery plan for project managers and planners.
Additional Information
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 8
Schedule Data Management
Handles the upload, parsing, validation, and preprocessing of construction schedule data, including activities, durations, dependencies, and resources.
2. Disruption Impact Analysis
Identifies schedule disruptions and analyzes their impact on affected activities and overall project completion.
Modules to Cover
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System

## Slide 9
3. Recovery Plan Generation & Optimization
Generates alternative recovery strategies and uses OR-Tools to find feasible and optimized recovery schedules.
4. Agentic AI Recommendation & Explanation
Uses LangGraph and an LLM to coordinate the workflow, recommend the best recovery plan, and explain the decision.
Modules to Cover
Agentic AI-Based Construction Schedule Disruption Analysis and Recovery Planning System